## Sheet1
Town & Country Planning Organisation
Ministry of Urban Development
Govt. of India
Permanent Settlements in Andaman & Nicobar Islands
Status of Layout Plans, October, 2007
Sl. No. |  | Islands | *Reqd. of DUs | Tribal (T) / Non-Tribal (NT) | Status of Proposed Layout Plans | Area of Site (Ha.) | Density DU/Ha. | Remarks
1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8
A. | SOUTH ANDAMAN (823)
| 1 | Austinabad (Rev-3) | 168 |  | Completed - 106 | 4.45 | 23 | New Survey Site Plan required for 60 DUs.
| 2 | Bambooflat (Rev-3) | 373 | NT | Completed - 222 | 8.82 | 25 | New Survey Site Plan required for 151 DUs.
| 3 | Mithakhari | 29 |  | Completed - 52 | 6 | 9
| 4 | 2: Ograbraj; 3: 22
| 5 | Naya Saher | 73 |  | Completed - 72 | 2 | 36
| 6 | Sippighat | 19 |  | Completed - 19 | 0.5 | 38
| 7 | Teylarabad | 21 |  | Completed - 22 | 0.58 | 38
| 8 | Badmaspahar (Rev-1) | 99 | NT | Completed - 100 | 3.4 | 29
| 9 | Chidiyatapu | 19 |  | Completed - 28 | 0.5 | 56
B. | LITTLE ANDAMAN (1973)
| 1 | Harminder Bay (Rev-2) | 340 | T | Completed - 348 | 14 | 27
| 2 | Onge Tekri (Ph-I & Ph-II) | 965 |  | Completed - 965 | 40 | 24
| 3 | Farm Tekri (337) | 511 |  | Completed - 322 | 9.4 | 34 | New Survey Site Plan required for 189 DUs.
| 4 | Netaji Nagar | 157 | NT | Completed - 90 | 2 | 43 | New Survey Site Plan required for 67 DUs.
* As per A&N Administration Website
C. | CAR NICOBAR (3941)
| 1 | Perka | 411 | T | Completed - 411 | - | -
| 2 | Malacca | 240 | T | Completed - 240 | - | -
| 3 | Tamaloo | 332 | T | Completed - 332 | - | -
| 4 | Kinyuka | 271 | T | Completed - 271 | - | -
| 5 | Chuckchuka | 302 | T | Completed - 302 | - | -
| 6 | Tapoiming | 212 | T | Completed - 212 | - | -
| 7 | Big-lapathy | 256 | T | Completed - 255 | - | -
| 8 | Small-lapathy | 331 | T | Completed - 331 | - | -
| 9 | Kinmai | 184 | T | Completed - 184 | - | -
| 10 | Mus | 382 | T | Completed - 382 | - | -
| 11 | Sawai | 305 | T | Completed - 305 | - | -
| 12 | Tee-top | 105 | T | Completed - 105 | - | -
| 13 | Arong | 256 | T | Completed - 256 | - | -
| 14 | Kimious | 114 | T | Completed - 114 | - | -
| 15 | Kakana | 240 | T | Completed - 240 | - | -
D. | TERRESSA (506)
| 1 | kanhaminot | 14 | T | Completed - 12 | - | -
| 2 | Bengali | 96 | T | Completed - 86 | - | -
| 3 | Alurong | 68 | T | Completed - 64 | - | -
| 4 | Kalasi | 84 | T | Completed - 78 | - | -
| 5 | Chukmachi | 80 | T | Completed - 68 | - | -
| 6 | Minyuk | 68 | T | Completed - 64 | - | -
| 7 | Hinam | 56 | T | Completed - 56 | - | -
| 8 | Luxi | 40 | T | Completed - 38 | - | -
E. | KATCHAL (315)
| 1 | E-Wall (Wimco) | 36 | T | Completed - 36 | 1.1 | 33
| 2 | Sallo Tikri | 77 | T | Completed - 84 | 8.5 | 10
| 3 | Japan Tekri | 134 | NT | Completed - 90 | 4.51 | 20 | New Survey Site Plan required for 44 DUs.
| 4 | 2: Upper Katchal; 3: 68; 4: T; 8: Surey site plan awaited
* As per A&N Administration Website
F. | KAMORTA (518)
| 1 | Chota Enak | 44 | T | Completed - 36 | - | -
| 2 | Bada Enak & Safed Balu | 36 | T | Completed - 28 | - | -
| 3 | Vikas Nagar / Laful | 52 | T | Completed - 54 | - | -
| 4 | Kakana | 93 | T | Completed - 80 | - | -
| 5 | Pillpilow | 88 | T | Completed - 102 | - | -
| 6 | Daring | 42 | T | Completed - 64 | - | -
| 7 | Bunderkhari | 21 | T | Completed - 24 | - | -
| 8 | Changhua / Masala Tapu | 36 | T | Completed - 32 | - | -
| 9 | AL - UL - Heak | 45 | T | Completed - 12 | - | -
| 10 | Munak + Ramjav & Payuha | 61 | T | Completed - 46 | - | -
G. | NANCOWRIE (269)
| 1 | Champin | 119 | T | Completed - 132 | - | -
| 2 | Balubasti | 20 | T | Completed - 16 | - | -
| 3 | Tapong | 82 | T | Completed - 76 | - | -
| 4 | Hitui | 48 | T | Completed - 46 | - | -
H. | CHOWRA (346)
| 1 | Alheat | 56 | T | Completed | - | -
| 2 | Taeela | 100 | T | Completed | - | -
| 3 | Chongamong | 41 | T | Completed | - | -
| 4 | Kuitasuk | 75 | T | Completed | - | -
| 5 | Raiheon | 74 | T | Completed | - | -
* As per A&N Administration Website
I. | LITTLE NICOBAR (111)
| 1 | Makachuwa | 41 | T |  | - | - | Site Survey Plan Awaited.
| 2 | School Point |  | T |  | - | - | Site Survey Plan Awaited.
| 3 | Pillopanja | 28 | T |  | - | - | Site Survey Plan Awaited.
| 4 | Pillopatia | 4 | T |  | - | -
| 5 | Pillobha | 12 | T |  | - | - | Site Survey Plan Awaited.
| 6 | Pillollow | 26 | T |  | - | - | Site Survey Plan Awaited.
J. | GREAT NICOBAR (995)
| 1 | Campball Bay (RPRS) | 192 | T |  | 5 | - | Site Survey Plan Awaited.
| 2 | Campball Bay (F/Man Col.) | 106 | NT |  | 3 | - | Site Survey Plan Awaited.
| 3 | Govind Nagar | 59 | NT | Draft-58 | 1.52 | - | Site Survey Plan Awaited.
| 4 | Agri.Farm | 28 | NT |  |  | - | Site Survey Plan Awaited.
| 5 | Joginder Nagar | 267 | NT |  | 1.20 & 4.00 | - | Site Survey Plan Awaited.
| 6 | Laxmi Nagar | 75 | NT |  | 2 | - | Site Survey Plan Awaited.
| 7 | Gandhi Nagar | 152 | NT |  | 2.50 & 1.73 | - | Site Survey Plan Awaited.
| 8 | Shastri Nagar | 59 | NT |  | 1.8 & 1 | - | Site Survey Plan Awaited.
| 9 | Kopenheat | 22 | NT |  | - | - | Site Survey Plan Awaited.
| 10 | Afra Bay | 35 | NT |  | - | - | Site Survey Plan Awaited.
|  | Total | 9797
* As per A&N Administration Website

## Sheet2
ISLANDWISE STATUS OF PERMANENT SHELTERS
(LAYOUT PLAN OF PERMANENT SHELTERS PREPARED BY TCPO)
Name of the Islands | No. of Permanent Shelters to be Constructed by
| CPWD | APWD | NGO | TOTAL
South Andaman |  | 214 | 609 | 823
Little Andaman | 965 | 908 | 100 | 1973
Car Nicobar | 3941 |  |  | 3941
Teressa | 506 |  |  | 506
Katchal | 315 |  |  | 315
Kamorta | 518 |  |  | 518
Nancowry | 269 |  |  | 269
Chowra | 346 |  |  | 346
Little Nicobar | 111 |  |  | 111
Great Nicobar | 995 |  |  | 995
Total | 7966 | 1122 | 709 | 9797